## WBS
ID | Phase | Work Package | Activity | Best Effort (pd) | Likely Effort (pd) | Worst Effort (pd) | PERT Effort (pd) | Best Duration (d) | Likely Duration (d) | Worst Duration (d) | PERT Duration (d) | σ Duration | Resources | Dependencies | Risks | Notes | Billable | Billable PERT Effort
1 | Discovery & Design
1.1 |  | Discovery
1.1.1 |  |  | Stakeholder Workshops | 2 | 3 | 4 |  | 2 | 3 | 4 |  |  | DSG |  | R1 | Two half-day workshops | Y
1.1.2 |  |  | Heuristic Evaluation | 1 | 2 | 3 |  | 1 | 2 | 3 |  |  | DSG |  |  | Usability, accessibility, SEO baseline | Y
1.1.3 |  |  | Information Architecture | 1 | 2 | 3 |  | 1 | 2 | 3 |  |  | DSG | 1.1.1, 1.1.2 |  | Site map, navigation, URL structure | Y
1.2 |  | Design
1.2.1 |  |  | Wireframes | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | DSG | 1.1.3 |  | 8 page templates | Y
1.2.2 |  |  | High-Fidelity Mockups | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | DSG | 1.2.1 | R1 | Desktop and mobile breakpoints | Y
1.2.3 |  |  | Design Review & Sign-off | 1 | 2 | 4 |  | 1 | 2 | 4 |  |  | DSG | 1.2.2 | R1 | Two rounds of feedback | Y
2 | Development
2.1 |  | CMS & Templates
2.1.1 |  |  | CMS Setup & Theme Bootstrap | 1 | 2 | 3 |  | 1 | 2 | 3 |  |  | DEV | 1.2.3 |  | WordPress, Elementor Pro, base theme | Y
2.1.2 |  |  | Template Development | 5 | 8 | 12 |  | 5 | 8 | 12 |  |  | DEV | 2.1.1 |  | 8 reusable Elementor page layouts | Y
2.2 |  | Migration & Integrations
2.2.1 |  |  | Content Migration | 3 | 5 | 9 |  | 3 | 5 | 9 |  |  | DEV | 2.1.2 | R2 | 40 pages, 301 redirects | Y
2.2.2 |  |  | Integrations | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | DEV | 2.1.2 | R3 | CRM, GA4, cookie consent | Y
3 | Testing & Launch
3.1 |  | Quality Assurance
3.1.1 |  |  | QA & Accessibility Audit | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | DEV, DSG | 2.2.1, 2.2.2 |  | Cross-browser + WCAG 2.1 AA | Y
3.1.2 |  |  | Client UAT | 1 | 2 | 3 |  | 1 | 2 | 3 |  |  | DSG | 3.1.1 | R1 | Guided session + defect resolution | Y
3.2 |  | Launch
3.2.1 |  |  | Launch & Cutover | 1 | 1 | 2 |  | 1 | 1 | 2 |  |  | DEV | 3.1.2 |  | DNS cutover, SSL, smoke test, 48h monitoring | Y
TOTAL

## Resource Plan
Role | Code | Type | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | TOTAL (PD)
|  | Week of | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22
Developer | DEV | billable | 0 | 0 | 0 | 6.22 | 6.22 | 6.22 | 2.17 | 2.17
Designer | DSG | billable | 5.83 | 5.83 | 5.83 | 0 | 0 | 0 | 1 | 1
Weekly TOTAL
Capacity Warnings
Overcommit: W4 (DEV) (6.2 PD vs 5.0 PD capacity)
Overcommit: W5 (DEV) (6.2 PD vs 5.0 PD capacity)
Overcommit: W6 (DEV) (6.2 PD vs 5.0 PD capacity)
Overcommit: W1 (DSG) (5.8 PD vs 5.0 PD capacity)
Overcommit: W2 (DSG) (5.8 PD vs 5.0 PD capacity)
Overcommit: W3 (DSG) (5.8 PD vs 5.0 PD capacity)

## Risks
ID | Risk Description | Category | Affected Phases | Probability (1-5) | Impact (1-5) | Risk Score | Priority | Strategy | Mitigation Action | Owner | Contingency (pd) | Contingency Cost
R1 | Client delays sign-off on mockups, blocking development start | Organisational | 1, 2 | 3 | 4 |  |  | Mitigate | Define clear sign-off deadlines in contract; escalate after 3 business days | DSG | 4
R2 | Content migration takes longer due to inconsistent legacy data formats | Technical | 2 | 4 | 3 |  |  | Mitigate | Audit legacy content before migration; prepare transformation scripts | DEV | 3
R3 | Third-party CRM API changes require rework of contact form integration | External | 2 | 2 | 3 |  |  | Accept | Monitor CRM changelog; budget 1pd for emergency rework | DEV | 1
TOTAL
Management Reserve

## Summary
Phase | Description | Best Effort (pd) | Likely Effort (pd) | Worst Effort (pd) | PERT Effort (pd) | Best Duration (d) | Likely Duration (d) | Worst Duration (d) | PERT Duration (d) | σ Duration
Understand pain points, define visual identity, produce wireframes and mockups
Build CMS-driven website on WordPress + Elementor Pro
Validate quality, train client, execute DNS cutover
TOTAL
Tech PERT Effort (PD)
PM Overhead (+10%) (PD)
DevOps Overhead (+5%) (PD)
Subtotal Tech + Overhead (PD)
Contingency per-risk (PD)
Low Band
Management Reserve (10%) (PD)
Medium Band (recommended)
High Band
Total Billable Effort (PD)
Billable Ratio
Calendar Duration (weeks) | 8
Effort by Team (PD)
Agency | 42.5
Sensitivity Scenarios
Optimistic: ~85% of Fascia MEDIA — best-case execution for 1-website-redesign
Realistic: Fascia MEDIA — current best estimate including overhead and MR
Pessimistic: ~115% of Fascia MEDIA — material slippage on critical path