## WBS
ID | Phase | Work Package | Activity | Best Effort (pd) | Likely Effort (pd) | Worst Effort (pd) | PERT Effort (pd) | Best Duration (d) | Likely Duration (d) | Worst Duration (d) | PERT Duration (d) | σ Duration | Resources | Dependencies | Risks | Notes | Billable | Billable PERT Effort
1 | Assessment & Discovery
1.1 |  | Infrastructure Inventory
1.1.1 |  |  | Server and network inventory catalogue | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | CA, DE |  | R02 | Includes physical, virtual and cloud-native assets | Y
1.1.2 |  |  | Application dependency mapping | 4 | 7 | 12 |  | 4 | 7 | 12 |  |  | CA, DEV | 1.1.1 | R02, R04 | Dependency graph across all 12 applications | Y
1.1.3 |  |  | Licensing and compliance audit | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | PM, SE | 1.1.1 | R12, R14 | Software licences and regulatory obligations | Y
1.2 |  | Workload Assessment
1.2.1 |  |  | Application portfolio classification (6-R model) | 4 | 6 | 9 |  | 4 | 6 | 9 |  |  | CA, DEV | 1.1.2 | R06 | Rehost, Replatform, Refactor, Repurchase, Retire, Retain | Y
1.2.2 |  |  | TCO and ROI cloud analysis | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | PM | 1.2.1 | R12 |  | Y
1.2.3 |  |  | Risk and constraint identification | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | PM, CA | 1.1.3, 1.2.1 |  | Feeds into risk register | Y
2 | Cloud Architecture & Planning
2.1 |  | Architecture Design
2.1.1 |  |  | Landing zone and network topology design | 5 | 8 | 12 |  | 5 | 8 | 12 |  |  | CA, DE | 1.2.1 | R05, R08 | Multi-region architecture with hub-and-spoke topology | Y
2.1.2 |  |  | Identity and access management architecture | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | SE, CA | 2.1.1 | R07 | SSO, RBAC, zero-trust principles | Y
2.1.3 |  |  | Security controls and compliance framework | 4 | 6 | 10 |  | 4 | 6 | 10 |  |  | SE | 2.1.2 | R07, R14 | Aligned to CIS, NIST, GDPR controls | Y
2.1.4 |  |  | Disaster recovery and backup strategy | 3 | 4 | 6 |  | 3 | 4 | 6 |  |  | CA, DE | 2.1.1 | R13 | RTO/RPO targets to be agreed with client | Y
2.2 |  | Migration Planning
2.2.1 |  |  | Wave planning and sequence definition | 3 | 4 | 6 |  | 3 | 4 | 6 |  |  | CA, PM | 1.2.1, 2.1.1 | R06 | Dependency on 6-R classification output | Y
2.2.2 |  |  | Migration runbook per application (12 apps) | 8 | 12 | 18 |  | 8 | 12 | 18 |  |  | CA, DEV, DE | 2.2.1 | R02, R04 | One runbook per application, covering cutover steps and rollback | Y
2.2.3 |  |  | Rollback plan definition | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | DE, PM | 2.2.2 | R13 |  | Y
3 | Infrastructure Setup
3.1 |  | Landing Zone Provisioning
3.1.1 |  |  | Core account structure, policies and IAM bootstrap | 4 | 6 | 9 |  | 4 | 6 | 9 |  |  | DE, SE | 2.1.2, 2.1.3 | R05, R07 | IaC in Terraform | Y
3.1.2 |  |  | VPC/VNet configuration, peering and transit gateway | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | DE, CA | 3.1.1 | R08 |  | Y
3.1.3 |  |  | DNS, load balancers and CDN configuration | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | DE | 3.1.2 | R11 |  | Y
3.2 |  | Platform Services Configuration
3.2.1 |  |  | Kubernetes cluster setup and hardening | 5 | 8 | 12 |  | 5 | 8 | 12 |  |  | DE, SE | 3.1.2 | R04, R09 | EKS/AKS with node auto-scaling and PodSecurityPolicies | Y
3.2.2 |  |  | CI/CD pipeline infrastructure (GitOps with ArgoCD) | 4 | 6 | 9 |  | 4 | 6 | 9 |  |  | DE | 3.2.1 | R09 |  | Y
3.2.3 |  |  | Monitoring, logging and alerting stack (Prometheus/Grafana/ELK) | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | DE, SE | 3.2.1 |  |  | Y
3.2.4 |  |  | Secret management and certificate automation (Vault / ACM) | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | SE | 3.1.1 | R07 |  | Y
4 | Migration Wave 1
4.1 |  | Wave 1 Execution
4.1.1 |  |  | Containerisation and refactoring — Wave 1 apps (4) | 10 | 16 | 24 |  | 10 | 16 | 24 |  |  | DEV, DE | 3.2.1, 3.2.2 | R04 | Dockerfile, Helm charts, environment configuration | Y
4.1.2 |  |  | Data migration — Wave 1 databases | 5 | 8 | 14 |  | 5 | 8 | 14 |  |  | DE, DEV | 4.1.1 | R03 | Schema migration and data sync scripts | Y
4.1.3 |  |  | Integration re-wiring and smoke tests — Wave 1 | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | DEV, DE | 4.1.2 | R11 |  | Y
4.2 |  | Wave 1 Validation
4.2.1 |  |  | Functional regression tests — Wave 1 | 4 | 6 | 10 |  | 4 | 6 | 10 |  |  | DEV, PM | 4.1.3 |  |  | Y
4.2.2 |  |  | Performance baseline comparison — Wave 1 | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | DE, SE | 4.2.1 | R08 |  | Y
4.2.3 |  |  | Security scan and remediation — Wave 1 | 2 | 4 | 7 |  | 2 | 4 | 7 |  |  | SE | 4.2.1 | R07 | DAST/SAST scan + remediation cycle | Y
5 | Migration Wave 2
5.1 |  | Wave 2 Execution
5.1.1 |  |  | Containerisation and refactoring — Wave 2 apps (4) | 14 | 20 | 30 |  | 14 | 20 | 30 |  |  | DEV, DE | 4.2.3, 3.2.2 | R04, R10 | Higher complexity apps with more dependencies | Y
5.1.2 |  |  | Data migration — Wave 2 databases | 6 | 10 | 16 |  | 6 | 10 | 16 |  |  | DE, DEV | 5.1.1 | R03 | Larger data volumes than Wave 1 | Y
5.1.3 |  |  | Integration re-wiring and smoke tests — Wave 2 | 4 | 6 | 10 |  | 4 | 6 | 10 |  |  | DEV, DE | 5.1.2 | R11 |  | Y
5.2 |  | Wave 2 Validation
5.2.1 |  |  | Functional regression tests — Wave 2 | 5 | 8 | 12 |  | 5 | 8 | 12 |  |  | DEV, PM | 5.1.3 | R15 |  | Y
5.2.2 |  |  | Performance and load testing — Wave 2 | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | DE, SE | 5.2.1 | R08 |  | Y
5.2.3 |  |  | Security hardening review — Wave 2 | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | SE | 5.2.1 | R07 |  | Y
6 | Migration Wave 3
6.1 |  | Wave 3 Execution
6.1.1 |  |  | Legacy modernisation and containerisation — Wave 3 apps (4) | 18 | 28 | 42 |  | 18 | 28 | 42 |  |  | DEV, CA, DE | 5.2.3, 3.2.2 | R04, R10 | Includes rewriting legacy monolith components as microservices | Y
6.1.2 |  |  | Data migration — Wave 3 (large volumes, replication lag management) | 8 | 14 | 22 |  | 8 | 14 | 22 |  |  | DE, DEV | 6.1.1 | R03, R13 | Near-zero-downtime migration using CDC / log shipping | Y
6.1.3 |  |  | Integration re-wiring, API gateway config and smoke tests — Wave 3 | 5 | 8 | 13 |  | 5 | 8 | 13 |  |  | DEV, CA, DE | 6.1.2 | R11 |  | Y
6.2 |  | Wave 3 Validation
6.2.1 |  |  | Full regression suite — Wave 3 | 6 | 10 | 16 |  | 6 | 10 | 16 |  |  | DEV, PM | 6.1.3 | R15 |  | Y
6.2.2 |  |  | End-to-end cross-wave integration testing | 5 | 8 | 14 |  | 5 | 8 | 14 |  |  | CA, DEV, DE | 6.2.1 | R11 | Verifies all 12 migrated apps interact correctly | Y
6.2.3 |  |  | Security penetration testing | 4 | 6 | 10 |  | 4 | 6 | 10 |  |  | SE | 6.2.1 | R07 | External pen test plus internal remediation | Y
7 | Testing, Validation & Cutover
7.1 |  | Non-Functional Testing
7.1.1 |  |  | Full load and stress testing — all applications | 4 | 7 | 11 |  | 4 | 7 | 11 |  |  | DE, SE | 6.2.3 | R08 |  | Y
7.1.2 |  |  | Chaos engineering and resilience testing | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | DE, CA | 7.1.1 | R05 | Simulated availability zone failure and network partition | Y
7.2 |  | Acceptance Testing & Cutover
7.2.1 |  |  | UAT coordination and execution support | 4 | 6 | 10 |  | 4 | 6 | 10 |  |  | PM, DEV | 7.1.2 | R15 | Requires business key-user availability | Y
7.2.2 |  |  | Defect triage and remediation | 4 | 7 | 12 |  | 4 | 7 | 12 |  |  | DEV, DE | 7.2.1 | R04 |  | Y
7.2.3 |  |  | Go-live readiness sign-off and final cutover execution | 3 | 4 | 6 |  | 3 | 4 | 6 |  |  | PM, CA, DE | 7.2.2 | R05, R13 | Includes DNS cutover and traffic switch | Y
7.2.4 |  |  | Hypercare support and stabilisation (2 weeks) | 6 | 8 | 12 |  | 6 | 8 | 12 |  |  | DE, DEV, SE | 7.2.3 |  | On-call rotation, incident response and hotfix capability | Y
TOTAL

## Resource Plan
Role | Code | Type | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | TOTAL (PD)
|  | Week of | 2026-09-01 | 2026-09-08 | 2026-09-15 | 2026-09-22 | 2026-09-29 | 2026-10-06 | 2026-10-13 | 2026-10-20 | 2026-10-27 | 2026-11-03 | 2026-11-10 | 2026-11-17 | 2026-11-24 | 2026-12-01 | 2026-12-08 | 2026-12-15 | 2026-12-22 | 2026-12-29 | 2027-01-05 | 2027-01-12 | 2027-01-19 | 2027-01-26 | 2027-02-02 | 2027-02-09 | 2027-02-16 | 2027-02-23 | 2027-03-02 | 2027-03-09 | 2027-03-16 | 2027-03-23 | 2027-03-30 | 2027-04-06 | 2027-04-13 | 2027-04-20 | 2027-04-27 | 2027-05-04 | 2027-05-11 | 2027-05-18 | 2027-05-25 | 2027-06-01 | 2027-06-08 | 2027-06-15 | 2027-06-22 | 2027-06-29 | 2027-07-06 | 2027-07-13 | 2027-07-20 | 2027-07-27 | 2027-08-03 | 2027-08-10
Cloud Architect | CA | billable | 4.67 | 4.67 | 4.67 | 4.67 | 4.81 | 4.81 | 4.81 | 4.81 | 4.81 | 4.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0
DevOps Engineer | DE | billable | 0 | 0 | 0 | 0 | 0.53 | 0.53 | 0.53 | 0.53 | 0.53 | 0.53 | 4.86 | 4.86 | 4.86 | 4.86 | 4.86 | 4.86 | 4.86 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 3.44 | 3.44 | 3.44 | 3.44 | 3.44 | 3.44
Developer | DEV | billable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 | 3.91 | 3.91 | 3.91 | 3.91 | 3.91 | 3.91 | 3.91 | 3.91 | 3.91 | 4.73 | 4.73 | 4.73 | 4.73 | 4.73 | 4.73 | 4.73 | 4.73 | 4.73 | 4.73 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22
Project Manager | PM | billable | 2.38 | 2.38 | 2.38 | 2.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75
Security Engineer | SE | billable | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0 | 0 | 0 | 0 | 0 | 0
Weekly TOTAL

## Risks
ID | Risk Description | Category | Affected Phases | Probability (1-5) | Impact (1-5) | Risk Score | Priority | Strategy | Mitigation Action | Owner | Contingency (pd) | Contingency Cost
R01 | Cloud Architect resource unavailability due to market competition | Organizational | 1, 2, 3 | 4 | 5 |  |  | Mitigate | Dual-source cloud architects; include bench resource in contract; knowledge redundancy through pair working | PM | 20
R02 | Application dependency complexity exceeds initial assessment estimates | Technical | 1, 2 | 5 | 4 |  |  | Mitigate | Automated dependency scanning tools; allow buffer time in assessment phase; iterative discovery | CA | 18
R03 | Data migration volume or quality issues causing delays | Technical | 4, 5, 6 | 4 | 5 |  |  | Mitigate | Early data profiling; automated data quality scripts; dry-run migrations before production cutover | DE | 25
R04 | Legacy application incompatibility with containerisation approach | Technical | 4, 5, 6, 7 | 4 | 4 |  |  | Mitigate | Technical spike in Phase 1; fallback to VM-based lift-and-shift for incompatible apps; 6-R reclassification | CA | 30
R05 | Cloud provider service outage or degradation during active migration window | External | 3, 4, 7 | 3 | 5 |  |  | Accept | Monitor cloud provider status page; schedule cutover windows during low-risk periods; multi-region failover design | DE | 10
R06 | Scope creep from late-discovered applications not in original inventory | Scope | 1, 2 | 4 | 3 |  |  | Mitigate | Strict scope freeze after Phase 1 sign-off; formal change control board; contractual scope boundary clause | PM | 15
R07 | Security compliance gap identified in hardened cloud environment | Security | 3, 4, 5, 6 | 3 | 4 |  |  | Mitigate | Cloud Security Posture Management (CSPM) tool from day one; automated policy-as-code enforcement; quarterly security reviews | SE | 12
R08 | Network performance degradation post-migration due to latency or bandwidth issues | Technical | 4, 5, 6, 7 | 3 | 4 |  |  | Mitigate | Network baseline measurement before migration; performance SLA defined; CDN and caching optimisation | DE | 8
R09 | CI/CD pipeline instability blocking deployments | Technical | 3, 4 | 3 | 3 |  |  | Mitigate | Pipeline validation gates; blue-green deployment fallback; dedicated pipeline engineer during setup | DE | 6
R10 | Key personnel departure during critical migration waves | Organizational | 5, 6 | 3 | 4 |  |  | Mitigate | Knowledge documentation and runbooks maintained continuously; bench resource pre-identified; retention incentives | PM | 16
R11 | Third-party integrations not compatible with new cloud endpoints | External | 4, 5, 6 | 4 | 3 |  |  | Mitigate | API contract testing in parallel with migration; stub servers for dependent systems; early vendor engagement | CA | 12
R12 | Unexpected licensing costs from cloud services exceeding budget | Financial | 1, 3 | 3 | 3 |  |  | Accept | Reserved instance pricing; tagging strategy for cost allocation; monthly FinOps review; budget alerts | PM | 5
R13 | Inadequate rollback capability for Wave 3 critical applications | Technical | 6, 7 | 3 | 5 |  |  | Mitigate | Full rollback plan tested in rehearsal; parallel-run mode for critical apps before DNS cutover; data replication maintained | CA | 20
R14 | Regulatory or compliance audit triggered mid-migration | External | 2, 3 | 2 | 4 |  |  | Accept | Proactive compliance documentation; maintain audit trail of all infrastructure changes; pre-engage compliance officer | PM | 8
R15 | Client stakeholder unavailability for UAT sign-off causing schedule slippage | Organizational | 5, 6, 7 | 3 | 3 |  |  | Mitigate | Formal UAT participation agreement; dedicated UAT coordination resource; asynchronous review tooling | PM | 8
TOTAL
Management Reserve

## Summary
Phase | Description | Best Effort (pd) | Likely Effort (pd) | Worst Effort (pd) | PERT Effort (pd) | Best Duration (d) | Likely Duration (d) | Worst Duration (d) | PERT Duration (d) | σ Duration
Inventory and assess current-state infrastructure and application portfolio
Design the target cloud architecture and produce the detailed migration plan
Provision and configure the target cloud landing zone and platform services
Migrate 4 lower-complexity applications to the cloud environment
Migrate 4 medium-complexity applications to the cloud environment
Migrate 4 high-complexity, business-critical applications to cloud
System-wide non-functional testing, UAT, production cutover and hypercare stabilisation
TOTAL
Tech PERT Effort (PD)
PM Overhead (+10%) (PD)
DevOps Overhead (+5%) (PD)
Subtotal Tech + Overhead (PD)
Contingency per-risk (PD)
Low Band
Management Reserve (20%) (PD)
Medium Band (recommended)
High Band
Total Billable Effort (PD)
Billable Ratio
Calendar Duration (weeks) | 50
Effort by Team (PD)
Management | 20
Technical | 303.3333
Sensitivity Scenarios
Optimistic: ~85% of Fascia MEDIA — best-case execution for 4-cloud-migration
Realistic: Fascia MEDIA — current best estimate including overhead and MR
Pessimistic: ~115% of Fascia MEDIA — material slippage on critical path