## WBS
ID | Phase | Work Package | Activity | Best Effort (pd) | Likely Effort (pd) | Worst Effort (pd) | PERT Effort (pd) | Best Duration (d) | Likely Duration (d) | Worst Duration (d) | PERT Duration (d) | σ Duration | Resources | Dependencies | Risks | Notes | Billable | Billable PERT Effort
1 | Analysis
1.1 |  | Requirements
1.1.1 |  |  | Stakeholder interviews | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | PM, SD |  | R1 | Key stakeholder availability required | Y
1.1.2 |  |  | Requirements documentation | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | SD | 1.1.1 |  |  | Y
1.2 |  | Technical Assessment
1.2.1 |  |  | Architecture review | 2 | 3 | 5 |  | 2 | 3 | 4 |  |  | SD | 1.1.1 | R2 |  | Y
1.2.2 |  |  | Risk assessment | 1 | 2 | 3 |  | 1 | 2 | 3 |  |  | PM | 1.2.1 |  |  | Y
2 | Design & Development
2.1 |  | Design
2.1.1 |  |  | System design | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | SD | 1.1.2, 1.2.1 | R2 | Architecture decisions impact all downstream work | Y
2.1.2 |  |  | Database schema design | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | SD | 2.1.1 |  |  | Y
2.2 |  | Implementation
2.2.1 |  |  | Backend development | 8 | 12 | 18 |  | 8 | 12 | 18 |  |  | SD | 2.1.2 | R1, R3 | Core API and business logic implementation | Y
2.2.2 |  |  | Frontend development | 5 | 8 | 12 |  | 5 | 8 | 12 |  |  | SD | 2.1.1 | R3 |  | Y
3 | Testing & Deployment
3.1 |  | Testing
3.1.1 |  |  | Unit testing | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | QA, SD | 2.2.1, 2.2.2 |  |  | Y
3.1.2 |  |  | Integration testing | 3 | 4 | 7 |  | 3 | 4 | 7 |  |  | QA | 3.1.1 | R4 | External service dependencies may slow this | Y
3.2 |  | Release
3.2.1 |  |  | UAT | 2 | 3 | 6 |  | 2 | 3 | 6 |  |  | PM, QA | 3.1.2 | R1, R4 | Client sign-off required before deployment | Y
3.2.2 |  |  | Deployment | 1 | 2 | 4 |  | 1 | 2 | 4 |  |  | SD | 3.2.1 |  | Deployment window must be coordinated with ops team | Y
TOTAL

## Resource Plan
Role | Code | Type | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | TOTAL (PD)
|  | Week of | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22
Project Manager | PM | billable | 3.58 | 3.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0.83 | 0.83 | 0.83 | 0.83
QA Engineer | QA | billable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.38 | 2.38 | 2.38 | 2.38
Senior Developer | SD | billable | 3.17 | 3.17 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.66 | 0.54 | 0.54 | 0.54
Weekly TOTAL

## Risks
ID | Risk Description | Category | Affected Phases | Probability (1-5) | Impact (1-5) | Risk Score | Priority | Strategy | Mitigation Action | Owner | Contingency (pd) | Contingency Cost
R1 | Key resource unavailable due to illness or turnover | Organizational | 1, 2, 3 | 3 | 4 |  |  | Mitigate | Cross-train team members and maintain knowledge base | PM | 5
R2 | Requirements change mid-project due to regulatory updates | External | 1, 2 | 4 | 3 |  |  | Accept | Budget for change requests and maintain flexible architecture | PM | 8
R3 | Third-party API integration complexity underestimated | Technical | 2 | 3 | 3 |  |  | Mitigate | Prototype integration early and allocate spike time | SD | 4
R4 | UAT delayed due to client availability or environment issues | External | 3 | 4 | 4 |  |  | Mitigate | Agree on UAT schedule and environment setup checklist upfront | PM | 6
TOTAL
Management Reserve

## Summary
Phase | Description | Best Effort (pd) | Likely Effort (pd) | Worst Effort (pd) | PERT Effort (pd) | Best Duration (d) | Likely Duration (d) | Worst Duration (d) | PERT Duration (d) | σ Duration
Requirements analysis and planning
System design and implementation
Quality assurance and production rollout
TOTAL
Tech PERT Effort (PD)
PM Overhead (+10%) (PD)
DevOps Overhead (+5%) (PD)
Subtotal Tech + Overhead (PD)
Contingency per-risk (PD)
Low Band
Management Reserve (10%) (PD)
Medium Band (recommended)
High Band
Total Billable Effort (PD)
Billable Ratio
Calendar Duration (weeks) | 12
Effort by Team (PD)
Development | 46.8333
Management | 10.5
Sensitivity Scenarios
Optimistic: 75 PD if stakeholder availability is high and no requirement changes occur
Realistic: 92 PD (Fascia MEDIA) with current overhead and MR assumptions
Pessimistic: 110 PD if external API integration delays force rework