## WBS
ID | Phase | Work Package | Activity | Best Effort (pd) | Likely Effort (pd) | Worst Effort (pd) | PERT Effort (pd) | Best Duration (d) | Likely Duration (d) | Worst Duration (d) | PERT Duration (d) | σ Duration | Resources | Dependencies | Risks | Notes | Billable | Billable PERT Effort
1 | Discovery & Project Setup
1.1 |  | Project Initiation
1.1.1 |  |  | Kickoff meeting and stakeholder alignment | 2 | 3 | 4 |  | 2 | 3 | 4 |  |  | PMO, BDM |  | R06 |  | Y
1.1.2 |  |  | Project charter and governance model definition | 3 | 4 | 6 |  | 3 | 4 | 6 |  |  | PMO | 1.1.1 |  |  | Y
1.1.3 |  |  | Tool and environment setup (Jira, Confluence, VPN, dev sandbox) | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | SRE |  | R11 | Cloud provisioning dependent on vendor SLA | Y
1.2 |  | Current Landscape Assessment
1.2.1 |  |  | Inventory of existing ERP modules and custom objects | 4 | 6 | 9 |  | 4 | 6 | 9 |  |  | SAP, BDM | 1.1.2 | R07 |  | Y
1.2.2 |  |  | Technical infrastructure assessment (servers, DB, integrations) | 3 | 5 | 7 |  | 3 | 5 | 7 |  |  | SRE, DA | 1.1.2 | R04 |  | Y
2 | As-Is Analysis
2.1 |  | Business Process Documentation
2.1.1 |  |  | Finance process mapping (FI/CO) | 6 | 8 | 12 |  | 6 | 8 | 12 |  |  | BDM, SAP | 1.2.1 | R03 |  | Y
2.1.2 |  |  | Logistics and warehouse process mapping (MM/WM/PP) | 5 | 7 | 10 |  | 5 | 7 | 10 |  |  | BDM, SAP | 1.2.1 | R03 |  | Y
2.1.3 |  |  | HR process documentation (HCM) | 3 | 5 | 7 |  | 3 | 5 | 7 |  |  | BDM | 1.2.1 |  |  | Y
2.2 |  | Technical Gap Analysis
2.2.1 |  |  | Custom ABAP code inventory and complexity scoring | 5 | 8 | 14 |  | 5 | 8 | 14 |  |  | SAP | 1.2.1 | R07 | Complexity depends on number of custom Z-objects found | Y
2.2.2 |  |  | Integration interfaces catalogue (EDI, port systems, customs) | 4 | 6 | 9 |  | 4 | 6 | 9 |  |  | SAP, DA | 1.2.2 | R05 |  | Y
3 | To-Be Design
3.1 |  | Solution Architecture
3.1.1 |  |  | Target architecture blueprint (cloud topology, tenancy model) | 5 | 7 | 10 |  | 5 | 7 | 10 |  |  | SRE, SAP | 2.2.1, 2.2.2 | R04, R11 |  | Y
3.1.2 |  |  | Integration design — BTP middleware and API gateway | 6 | 8 | 12 |  | 6 | 8 | 12 |  |  | SAP, DA | 3.1.1 | R05 |  | Y
3.1.3 |  |  | Security and authorisation model design | 3 | 4 | 6 |  | 3 | 4 | 6 |  |  | SRE | 3.1.1 |  |  | Y
3.2 |  | Functional Design
3.2.1 |  |  | Process redesign workshops (Finance, Logistics, HR) | 8 | 12 | 18 |  | 8 | 12 | 18 |  |  | BDM, SAP | 2.1.1, 2.1.2, 2.1.3 | R03, R06 | Requires full stakeholder availability | Y
3.2.2 |  |  | Configuration workbook and delta design document | 5 | 7 | 10 |  | 5 | 7 | 10 |  |  | BDM, SAP | 3.2.1 |  |  | Y
4 | Data Migration
4.1 |  | Data Migration Strategy
4.1.1 |  |  | Data objects catalogue and migration approach per object | 5 | 7 | 10 |  | 5 | 7 | 10 |  |  | DA, SAP | 2.2.1 | R02 |  | Y
4.1.2 |  |  | Data quality assessment and cleansing rules definition | 6 | 10 | 18 |  | 6 | 10 | 18 |  |  | DA | 4.1.1 | R02 | Legacy data quality is the primary risk driver | Y
4.2 |  | ETL Build & Dry-Run
4.2.1 |  |  | Extraction scripts and LTMC/BODS mapping | 8 | 12 | 18 |  | 8 | 12 | 18 |  |  | DA, SAP | 4.1.2 | R02, R07 |  | Y
4.2.2 |  |  | Data cleansing and transformation routines | 5 | 8 | 14 |  | 5 | 8 | 14 |  |  | DA | 4.2.1 | R02 |  | Y
4.2.3 |  |  | Dry-run execution and reconciliation report | 4 | 6 | 10 |  | 4 | 6 | 10 |  |  | DA, SAP | 4.2.2 | R09 |  | Y
5 | Development
5.1 |  | System Configuration
5.1.1 |  |  | S/4HANA system configuration (Finance module) | 10 | 14 | 20 |  | 10 | 14 | 20 |  |  | SAP | 3.2.2 | R04 |  | Y
5.1.2 |  |  | S/4HANA system configuration (Logistics and Operations modules) | 10 | 14 | 20 |  | 10 | 14 | 20 |  |  | SAP | 3.2.2 | R04 |  | Y
5.2 |  | Custom Development
5.2.1 |  |  | Custom RICEF objects (Reports, Interfaces, Conversions, Enhancements, Forms) | 14 | 20 | 30 |  | 14 | 20 | 30 |  |  | SAP | 5.1.1, 5.1.2 | R07, R01 | Volume depends on custom code inventory findings | Y
5.2.2 |  |  | BTP integration flows and API adaptors | 8 | 12 | 18 |  | 8 | 12 | 18 |  |  | SAP, DA | 3.1.2 | R05 |  | Y
5.2.3 |  |  | Port authority-specific extensions and PCS connector | 6 | 9 | 14 |  | 6 | 9 | 14 |  |  | SAP | 5.2.2 | R05 | Dependent on PCS vendor API documentation | Y
6 | Testing
6.1 |  | System & Integration Testing
6.1.1 |  |  | Unit and configuration testing | 5 | 8 | 12 |  | 5 | 8 | 12 |  |  | SAP | 5.1.1, 5.1.2, 5.2.1 |  |  | Y
6.1.2 |  |  | Integration testing (end-to-end process chains) | 8 | 12 | 18 |  | 8 | 12 | 18 |  |  | SAP, BDM | 6.1.1, 5.2.2, 5.2.3 | R05, R07 |  | Y
6.1.3 |  |  | Performance and load testing | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | SRE | 6.1.1 | R11 |  | Y
6.2 |  | User Acceptance Testing
6.2.1 |  |  | UAT planning and scenario preparation | 4 | 5 | 8 |  | 4 | 5 | 8 |  |  | BDM, PMO | 6.1.2 | R08 |  | Y
6.2.2 |  |  | UAT execution with key users | 6 | 10 | 16 |  | 6 | 10 | 16 |  |  | BDM, SAP | 6.2.1 | R08, R06 | Business key users must be available full time | Y
6.2.3 |  |  | Defect resolution and re-testing | 5 | 8 | 14 |  | 5 | 8 | 14 |  |  | SAP, BDM | 6.2.2 | R07 |  | Y
7 | Training
7.1 |  | Training Material Development
7.1.1 |  |  | Training curriculum design and role-based learning paths | 4 | 5 | 8 |  | 4 | 5 | 8 |  |  | TRN, BDM | 3.2.1 | R12 |  | Y
7.1.2 |  |  | eLearning modules and process simulations | 6 | 9 | 13 |  | 6 | 9 | 13 |  |  | TRN | 7.1.1 | R12 |  | Y
7.2 |  | Training Delivery
7.2.1 |  |  | Train-the-trainer sessions (super-users) | 4 | 5 | 7 |  | 4 | 5 | 7 |  |  | TRN, SAP | 7.1.2 | R06 |  | Y
7.2.2 |  |  | End-user classroom and virtual training sessions | 6 | 8 | 12 |  | 6 | 8 | 12 |  |  | TRN | 7.2.1 | R06 |  | Y
8 | Go-Live & Stabilisation
8.1 |  | Cutover Execution
8.1.1 |  |  | Final data migration (production cutover load) | 5 | 7 | 12 |  | 5 | 7 | 12 |  |  | DA, SAP | 4.2.3, 6.2.3 | R09, R02 |  | Y
8.1.2 |  |  | Go-live readiness checklist and sign-off | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | PMO, BDM | 8.1.1 |  |  | Y
8.1.3 |  |  | Production system activation and hypercare | 6 | 8 | 12 |  | 6 | 8 | 12 |  |  | SAP, SRE | 8.1.2 | R04, R10 | Two-week on-site hypercare team | Y
8.2 |  | Post Go-Live Support
8.2.1 |  |  | Hypercare support (2 weeks on-site) | 6 | 8 | 12 |  | 6 | 8 | 12 |  |  | SAP, SRE | 8.1.3 |  |  | Y
8.2.2 |  |  | Knowledge handover and operational documentation | 3 | 4 | 6 |  | 3 | 4 | 6 |  |  | PMO, SRE | 8.2.1 |  |  | Y
TOTAL

## Resource Plan
Role | Code | Type | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W54 | W55 | TOTAL (PD)
|  | Week of | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14
Business Design Manager | BDM | billable | 0 | 0 | 0 | 0 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data Architect | DA | billable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.88 | 1.88 | 1.88 | 1.88
Project Management Officer | PMO | billable | 1.79 | 1.79 | 1.79 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.83 | 1.83 | 1.83 | 1.83
SAP Consultant | SAP | billable | 1.54 | 1.54 | 1.54 | 1.54 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 1.39 | 1.39 | 1.39 | 1.39 | 1.39 | 1.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 6.45 | 3.22 | 3.22 | 3.22 | 3.22 | 3.22 | 3.22 | 3.22 | 3.22 | 3.22 | 0 | 0 | 0 | 0 | 0 | 0 | 4.17 | 4.17 | 4.17 | 4.17
Site Reliability Engineer | SRE | billable | 2.04 | 2.04 | 2.04 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Training Specialist | TRN | billable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.67 | 4.67 | 4.67 | 4.67 | 4.67 | 4.67 | 0 | 0 | 0 | 0
Weekly TOTAL
Capacity Warnings
Overcommit: W26 (SAP) (6.5 PD vs 5.0 PD capacity)
Overcommit: W27 (SAP) (6.5 PD vs 5.0 PD capacity)
Overcommit: W28 (SAP) (6.5 PD vs 5.0 PD capacity)
Overcommit: W29 (SAP) (6.5 PD vs 5.0 PD capacity)
Overcommit: W30 (SAP) (6.5 PD vs 5.0 PD capacity)
Overcommit: W31 (SAP) (6.5 PD vs 5.0 PD capacity)
Overcommit: W32 (SAP) (6.5 PD vs 5.0 PD capacity)
Overcommit: W33 (SAP) (6.5 PD vs 5.0 PD capacity)
Overcommit: W34 (SAP) (6.5 PD vs 5.0 PD capacity)
Overcommit: W35 (SAP) (6.5 PD vs 5.0 PD capacity)
Overcommit: W36 (SAP) (6.5 PD vs 5.0 PD capacity)

## Risks
ID | Risk Description | Category | Affected Phases | Probability (1-5) | Impact (1-5) | Risk Score | Priority | Strategy | Mitigation Action | Owner | Contingency (pd) | Contingency Cost
R01 | Key SAP consultant unavailable due to market competition | Organizational | 5, 6 | 4 | 5 |  |  | Mitigate | Dual-source SAP consultants; include bench resource in contract | PMO | 20
R02 | Legacy data quality worse than expected (duplicate/corrupt records) | Technical | 4, 8 | 5 | 4 |  |  | Mitigate | Early data profiling in phase 2; automated data quality rules | DA | 25
R03 | Business process scope creep from stakeholder workshops | Scope | 2, 3 | 4 | 4 |  |  | Mitigate | Change control board; strict scope freeze after Phase 3 sign-off | PMO | 18
R04 | S/4HANA cloud release breaking existing configuration | Technical | 5, 8 | 3 | 4 |  |  | Mitigate | Subscribe to SAP release notes; enforce non-productive system upgrade testing | SAP | 8
R05 | Integration with Port Community System delayed by third party | External | 3, 5, 6 | 4 | 3 |  |  | Accept | Maintain interface stub for testing; escalate to contract management if delayed beyond threshold | PMO | 10
R06 | End-user resistance to new processes (change management failure) | Organizational | 3, 6, 7 | 3 | 4 |  |  | Mitigate | Dedicated change management stream; early super-user programme; communications plan | BDM | 12
R07 | ABAP custom code incompatibility with S/4HANA (deprecated APIs) | Technical | 2, 5, 6 | 4 | 3 |  |  | Mitigate | SAP Readiness Check early execution; remediation budget reserved | SAP | 14
R08 | Inadequate UAT participation from business key users | Organizational | 6 | 3 | 3 |  |  | Mitigate | Formal UAT participation agreement signed by business owners; flexible scheduling | BDM | 6
R09 | Data migration dry-run failures causing timeline slippage | Technical | 4, 8 | 3 | 3 |  |  | Mitigate | Two dress rehearsal migrations planned; automated reconciliation scripts | DA | 8
R10 | Regulatory or customs authority system changes affecting interfaces | External | 8 | 2 | 4 |  |  | Accept | Monitor regulatory calendar; include contingency days in cutover plan | PMO | 5
R11 | Cloud infrastructure provisioning delays | Technical | 1, 3 | 2 | 3 |  |  | Mitigate | Place provisioning order at contract signature; SLA tracked weekly | SRE | 4
R12 | Training material not ready in time for UAT phase | Schedule | 7 | 2 | 2 |  |  | Accept | Parallel development of training materials starting in Phase 3 | TRN | 3
TOTAL
Management Reserve

## Summary
Phase | Description | Best Effort (pd) | Likely Effort (pd) | Worst Effort (pd) | PERT Effort (pd) | Best Duration (d) | Likely Duration (d) | Worst Duration (d) | PERT Duration (d) | σ Duration
Establish project governance, tooling and baseline understanding
Deep-dive documentation of current business processes and technical landscape
Architectural and functional design of the target S/4HANA environment
Design, build and execute data extraction, transformation and load activities
Build of configuration, custom extensions and integration components
Structured testing cycle from unit through to User Acceptance Testing
Knowledge transfer and end-user enablement programme
Production cutover and post-go-live hypercare support
TOTAL
Tech PERT Effort (PD)
PM Overhead (+10%) (PD)
DevOps Overhead (+5%) (PD)
Subtotal Tech + Overhead (PD)
Contingency per-risk (PD)
Low Band
Management Reserve (15%) (PD)
Medium Band (recommended)
High Band
Total Billable Effort (PD)
Billable Ratio
Calendar Duration (weeks) | 55
Effort by Team (PD)
Development | 198.3333
Management | 70.1667
Operations | 52.6667
Sensitivity Scenarios
Optimistic: ~85% of Fascia MEDIA — best-case execution for 2-erp-migration
Realistic: Fascia MEDIA — current best estimate including overhead and MR
Pessimistic: ~115% of Fascia MEDIA — material slippage on critical path