## WBS
ID | Phase | Work Package | Activity | Best Effort (pd) | Likely Effort (pd) | Worst Effort (pd) | PERT Effort (pd) | Best Duration (d) | Likely Duration (d) | Worst Duration (d) | PERT Duration (d) | σ Duration | Resources | Dependencies | Risks | Notes | Billable | Billable PERT Effort
1 | Discovery
1.1 |  | Project Kickoff
1.1.1 |  |  | Stakeholder workshop | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | PO |  | R5 | Kick-off with key stakeholders | Y
1.1.2 |  |  | Requirements elicitation | 4 | 6 | 10 |  | 3 | 5 | 8 |  |  | PO, BED | 1.1.1 | R5 | User stories and acceptance criteria | Y
1.2 |  | Technical Feasibility
1.2.1 |  |  | Technology stack selection | 1 | 2 | 3 |  | 1 | 2 | 3 |  |  | MOB, BED | 1.1.2 |  | React Native vs Flutter evaluation | Y
1.2.2 |  |  | Architecture draft | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | BED | 1.2.1 | R2 | High-level system architecture | Y
2 | UX Design
2.1 |  | Wireframing
2.1.1 |  |  | User flow mapping | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | PO | 1.1.2 | R5 | Journey maps for field technicians | Y
2.1.2 |  |  | Low-fidelity wireframes | 4 | 6 | 9 |  | 3 | 4 | 6 |  |  | MOB, PO | 2.1.1 |  | Sketch-level wireframes for all screens | Y
2.2 |  | Prototyping
2.2.1 |  |  | Interactive prototype | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | MOB | 2.1.2 |  | Clickable prototype in Figma | Y
2.2.2 |  |  | Usability review | 2 | 3 | 5 |  | 1 | 2 | 4 |  |  | PO, QA | 2.2.1 |  | Internal review of prototype flows | Y
2.2.3 |  |  | Design iteration | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | MOB | 2.2.2 |  | Apply feedback from usability review | Y
3 | Backend Development
3.1 |  | Core API
3.1.1 |  |  | Auth and user management API | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | BED | 1.2.2 |  | JWT-based auth, role management | Y
3.1.2 |  |  | Work order CRUD API | 4 | 6 | 10 |  | 4 | 6 | 10 |  |  | BED | 3.1.1 | R2 | Full CRUD with offline conflict resolution | Y
3.1.3 |  |  | File upload API | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | BED | 3.1.1 |  | Photo and document upload endpoint | Y
3.2 |  | Infrastructure
3.2.1 |  |  | Cloud environment setup | 2 | 3 | 4 |  | 2 | 3 | 4 |  |  | BED | 1.2.2 |  | AWS/GCP provisioning, CI/CD pipelines | Y
3.2.2 |  |  | Push notification service | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | BED, MOB | 3.2.1 | R4 | FCM/APNs integration | Y
3.2.3 |  |  | Backend integration tests | 3 | 4 | 7 |  | 3 | 4 | 7 |  |  | QA, BED | 3.1.2, 3.1.3 |  | API contract testing and regression suite | Y
4 | Mobile Development
4.1 |  | Core Features
4.1.1 |  |  | Offline data sync module | 4 | 6 | 10 |  | 4 | 6 | 10 |  |  | MOB | 3.1.2 | R2 | SQLite local store, sync queue | Y
4.1.2 |  |  | Work order UI | 5 | 7 | 12 |  | 5 | 7 | 12 |  |  | MOB | 2.2.3, 3.1.2 | R6 | Create, view, update work orders on device | Y
4.1.3 |  |  | Photo and signature capture | 3 | 4 | 7 |  | 3 | 4 | 7 |  |  | MOB | 4.1.2 | R6 | Camera integration, signature pad | Y
4.2 |  | Integration and Testing
4.2.1 |  |  | Backend integration | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | MOB, BED | 4.1.1, 3.2.2 | R2 | End-to-end API wiring with mobile app | Y
4.2.2 |  |  | Mobile E2E testing | 4 | 5 | 8 |  | 4 | 5 | 8 |  |  | QA | 4.1.3, 4.2.1 | R6 | Device farm, iOS + Android regression | Y
5 | Launch
5.1 |  | Release
5.1.1 |  |  | App store submission | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | MOB, PO | 4.2.2 | R1 | iOS App Store + Google Play submission | Y
5.1.2 |  |  | UAT with pilot users | 3 | 4 | 6 |  | 3 | 4 | 6 |  |  | QA, PO | 5.1.1 | R5 | Pilot group of 10 field technicians | Y
5.1.3 |  |  | Go-live and monitoring | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | BED, MOB | 5.1.2 |  | Production deployment, alerting dashboards | Y
TOTAL

## Resource Plan
Role | Code | Type | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | TOTAL (PD)
|  | Week of | 2026-07-01 | 2026-07-08 | 2026-07-15 | 2026-07-22 | 2026-07-29 | 2026-08-05 | 2026-08-12 | 2026-08-19 | 2026-08-26 | 2026-09-02 | 2026-09-09 | 2026-09-16 | 2026-09-23 | 2026-09-30 | 2026-10-07 | 2026-10-14
Backend Dev | BED | billable | 1.58 | 1.58 | 0 | 0 | 0 | 5.21 | 5.21 | 5.21 | 5.21 | 0 | 0 | 0 | 0 | 0 | 1.58 | 1.58
Mobile Dev | MOB | billable | 1 | 1 | 4.83 | 4.83 | 4.83 | 0 | 0 | 0 | 0 | 4.67 | 4.67 | 4.67 | 4.67 | 4.67 | 1.58 | 1.58
Product Owner | PO | billable | 4.75 | 4.75 | 2.11 | 2.11 | 2.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA Engineer | QA | billable | 0 | 0 | 0 | 0 | 0 | 1.08 | 1.08 | 1.08 | 1.08 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 2.08 | 2.08
Weekly TOTAL
Capacity Warnings
Overcommit: W6 (BED) (5.2 PD vs 5.0 PD capacity)
Overcommit: W7 (BED) (5.2 PD vs 5.0 PD capacity)
Overcommit: W8 (BED) (5.2 PD vs 5.0 PD capacity)
Overcommit: W9 (BED) (5.2 PD vs 5.0 PD capacity)

## Risks
ID | Risk Description | Category | Affected Phases | Probability (1-5) | Impact (1-5) | Risk Score | Priority | Strategy | Mitigation Action | Owner | Contingency (pd) | Contingency Cost
R1 | App store approval delays | External | 5 | 3 | 3 |  |  | Mitigate | Submit early, prepare review guidelines, use TestFlight/internal track first | MOB | 3
R2 | Offline sync complexity underestimated | Technical | 3, 4 | 4 | 5 |  |  | Mitigate | Proof-of-concept spike in Discovery; adopt proven sync library | BED | 8
R3 | Key mobile developer unavailability | Organizational | 4 | 2 | 5 |  |  | Mitigate | Cross-train backend developer on mobile framework | PO | 10
R4 | Third-party push notification service outage | External | 3 | 2 | 3 |  |  | Accept | Monitor SLA; have fallback polling mechanism ready | BED | 2
R5 | Scope creep from stakeholder change requests | Organizational | 1, 2, 5 | 4 | 4 |  |  | Mitigate | Formal change control process; freeze scope after Phase 2 | PO | 6
R6 | iOS/Android compatibility fragmentation issues | Technical | 4 | 3 | 3 |  |  | Mitigate | Test on device farm from Phase 4 start; target OS versions ≥ iOS 15 / Android 11 | MOB | 4
TOTAL
Management Reserve

## Summary
Phase | Description | Best Effort (pd) | Likely Effort (pd) | Worst Effort (pd) | PERT Effort (pd) | Best Duration (d) | Likely Duration (d) | Worst Duration (d) | PERT Duration (d) | σ Duration
Stakeholder alignment, requirements elicitation and technical feasibility
User experience design, wireframing and interactive prototype
REST API implementation, infrastructure setup and backend testing
Native/cross-platform mobile app implementation and E2E testing
App store submission, UAT with pilot users and go-live
TOTAL
Tech PERT Effort (PD)
PM Overhead (+10%) (PD)
DevOps Overhead (+5%) (PD)
Subtotal Tech + Overhead (PD)
Contingency per-risk (PD)
Low Band
Management Reserve (10%) (PD)
Medium Band (recommended)
High Band
Total Billable Effort (PD)
Billable Ratio
Calendar Duration (weeks) | 16
Effort by Team (PD)
Engineering | 84
Product | 15.8333
Sensitivity Scenarios
Optimistic: ~85% of Fascia MEDIA — best-case execution for 3-mobile-app
Realistic: Fascia MEDIA — current best estimate including overhead and MR
Pessimistic: ~115% of Fascia MEDIA — material slippage on critical path