## WBS
ID | Phase | Work Package | Activity | Best Effort (hours) | Likely Effort (hours) | Worst Effort (hours) | PERT Effort (hours) | Best Duration (weeks) | Likely Duration (weeks) | Worst Duration (weeks) | PERT Duration (weeks) | σ Duration | Resources | Dependencies | Risks | Notes | Billable | Billable PERT Effort
1 | Diagnostic
1.1 |  | Current State Assessment
1.1.1 |  |  | Stakeholder Interviews | 32 | 40 | 56 |  | 1 | 2 | 3 |  |  | PRT, SC |  | R1, R2 | 20 structured interviews across 3 entities | Y
1.1.2 |  |  | Document & Process Review | 16 | 24 | 40 |  | 1 | 1 | 2 |  |  | SC, JC | 1.1.1 | R4 | Org charts, process maps, governance documents | Y
1.1.3 |  |  | Cultural & Change-Readiness Survey | 12 | 16 | 24 |  | 1 | 1 | 2 |  |  | SC |  |  | Design, administer and analyse 60-question survey | Y
1.2 |  | Gap Analysis
1.2.1 |  |  | Functional Redundancy Mapping | 16 | 24 | 40 |  | 1 | 1 | 2 |  |  | SC, JC | 1.1.2 |  | Cross-map roles and functions across 3 entities | Y
1.2.2 |  |  | Diagnostic Report | 12 | 16 | 24 |  | 1 | 1 | 2 |  |  | PRT, SC | 1.2.1 |  | Executive-ready consolidated findings report | Y
2 | Strategy Design
2.1 |  | Target Operating Model
2.1.1 |  |  | Design Workshops | 32 | 40 | 56 |  | 1 | 2 | 3 |  |  | PRT, SC | 1.2.2 | R1, R2 | 3 × full-day facilitated sessions with senior leadership | Y
2.1.2 |  |  | Org Structure Design | 32 | 40 | 64 |  | 1 | 2 | 3 |  |  | SC | 2.1.1 | R5 | Reporting lines, spans of control, role profiles | Y
2.1.3 |  |  | Governance & Decision Framework | 16 | 24 | 40 |  | 1 | 1 | 2 |  |  | SC, JC | 2.1.2 |  | RACI matrix, committee charters, escalation paths | Y
2.2 |  | Roadmap & Business Case
2.2.1 |  |  | Transformation Roadmap | 16 | 24 | 40 |  | 1 | 1 | 2 |  |  | SC, JC | 2.1.3 | R3 | Phased implementation plan, milestones, KPIs | Y
2.2.2 |  |  | Business Case & ROI Model | 16 | 24 | 40 |  | 1 | 1 | 2 |  |  | PRT, SC | 2.2.1 |  | Quantify savings, FTE impact, strategic value | Y
3 | Implementation Support
3.1 |  | Change Management
3.1.1 |  |  | Change Management Plan | 16 | 24 | 40 |  | 1 | 2 | 3 |  |  | SC, JC | 2.2.2 | R2 | Communications plan, training needs analysis, resistance management | Y
3.1.2 |  |  | Leadership Coaching Sessions | 12 | 16 | 24 |  | 2 | 3 | 5 |  |  | PRT | 3.1.1 | R1 | 6 sessions × 2 h with senior leaders | Y
3.2 |  | Process Re-engineering
3.2.1 |  |  | Priority Process Redesign | 32 | 40 | 64 |  | 2 | 3 | 5 |  |  | SC, JC | 2.2.2 | R3, R5 | Redesign 3 end-to-end cross-entity processes | Y
3.2.2 |  |  | Interim Performance Dashboard | 16 | 24 | 40 |  | 1 | 2 | 3 |  |  | SC, JC | 3.2.1 |  | Define and prototype management KPI dashboard | Y
4 | Knowledge Transfer
4.1 |  | Capability Building
4.1.1 |  |  | Playbook & Toolkit Delivery | 16 | 24 | 40 |  | 1 | 2 | 3 |  |  | SC, JC | 3.2.2 |  | Operating model playbook and toolkits for internal use | Y
4.1.2 |  |  | Train-the-Trainer Workshop | 12 | 16 | 24 |  | 1 | 1 | 2 |  |  | PRT, SC | 4.1.1 |  | 2-day internal facilitator training programme | Y
4.1.3 |  |  | Final Review & Sign-off Meeting | 6 | 8 | 12 |  | 1 | 1 | 1 |  |  | PRT, SC | 4.1.2 | R1 | Present final deliverables, capture lessons learned | Y
TOTAL

## Resource Plan
Role | Code | Type | W1 | W2 | W3 | W4 | W5 | W6 | TOTAL (PD)
|  | Week of | 2026-10-01 | 2026-10-08 | 2026-10-15 | 2026-10-22 | 2026-10-29 | 2026-11-05
Partner | PRT | billable | 58 | 33.33 | 33.33 | 8.33 | 8.33 | 25
Senior Consultant | SC | billable | 67.33 | 46.67 | 46.67 | 46.67 | 46.67 | 25.33
Weekly TOTAL
Capacity Warnings
Overcommit: W1 (PRT) (58.0 PD vs 5.0 PD capacity)
Overcommit: W2 (PRT) (33.3 PD vs 5.0 PD capacity)
Overcommit: W3 (PRT) (33.3 PD vs 5.0 PD capacity)
Overcommit: W4 (PRT) (8.3 PD vs 5.0 PD capacity)
Overcommit: W5 (PRT) (8.3 PD vs 5.0 PD capacity)
Overcommit: W6 (PRT) (25.0 PD vs 5.0 PD capacity)
Overcommit: W1 (SC) (67.3 PD vs 5.0 PD capacity)
Overcommit: W2 (SC) (46.7 PD vs 5.0 PD capacity)
Overcommit: W3 (SC) (46.7 PD vs 5.0 PD capacity)
Overcommit: W4 (SC) (46.7 PD vs 5.0 PD capacity)
Overcommit: W5 (SC) (46.7 PD vs 5.0 PD capacity)
Overcommit: W6 (SC) (25.3 PD vs 5.0 PD capacity)

## Risks
ID | Risk Description | Category | Affected Phases | Probability (1-5) | Impact (1-5) | Risk Score | Priority | Strategy | Mitigation Action | Owner | Contingency (hours) | Contingency Cost
R1 | Key client sponsor changes mid-engagement, disrupting strategic alignment | Organisational | 1, 2, 3, 4 | 3 | 5 |  |  | Mitigate | Establish multi-stakeholder governance; ensure project charter is signed at board level | PRT | 40
R2 | Resistance from legacy-org middle management delays workshop outcomes | Change | 1, 2 | 4 | 4 |  |  | Mitigate | Early engagement sessions with middle management; dedicated change champion network | SC | 32
R3 | Scope creep from additional integration requests not in original SoW | Commercial | 2, 3 | 4 | 3 |  |  | Mitigate | Strict change control process; weekly scope review with project sponsor | PRT | 24
R4 | Confidential data access restrictions slow diagnostic phase | Regulatory | 1 | 3 | 3 |  |  | Accept | Obtain NDA and data sharing agreements upfront; plan for desk-based alternatives | SC | 16
R5 | Key consultant unavailable during critical design workshops | Resource | 2, 3 | 2 | 4 |  |  | Mitigate | Maintain backup consultant briefed on engagement context; shadow shadowing programme | PRT | 24
TOTAL
Management Reserve

## Summary
Phase | Description | Best Effort (hours) | Likely Effort (hours) | Worst Effort (hours) | PERT Effort (hours) | Best Duration (weeks) | Likely Duration (weeks) | Worst Duration (weeks) | PERT Duration (weeks) | σ Duration
Assess current state of the three legacy organisations and identify gaps
Co-design the future operating model with senior leadership
Hands-on advisory support during first wave of transformation
Embed the new operating model and build internal capability
TOTAL
Tech PERT Effort (PD)
PM Overhead (+10%) (PD)
DevOps Overhead (+5%) (PD)
Subtotal Tech + Overhead (PD)
Contingency per-risk (PD)
Low Band
Management Reserve (10%) (PD)
Medium Band (recommended)
High Band
Total Billable Effort (PD)
Billable Ratio
Calendar Duration (weeks) | 6
Effort by Team (PD)
Consulting | 445.6667
Sensitivity Scenarios
Optimistic: ~85% of Fascia MEDIA — best-case execution for 5-consulting
Realistic: Fascia MEDIA — current best estimate including overhead and MR
Pessimistic: ~115% of Fascia MEDIA — material slippage on critical path