## WBS
ID | Phase | Work Package | Activity | Best Effort (pd) | Likely Effort (pd) | Worst Effort (pd) | PERT Effort (pd) | Best Duration (d) | Likely Duration (d) | Worst Duration (d) | PERT Duration (d) | σ Duration | Resources | Dependencies | Risks | Notes | Billable | Billable PERT Effort
F0 | Setup & Discovery
F0.1 |  | Project setup
F0.1.1 |  |  | Kickoff and governance setup | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | PM, BA |  |  |  | Y
F0.1.2 |  |  | Environment & access checklist | 1 | 2 | 3 |  | 1 | 2 | 3 |  |  | DEVOPS, TA |  | R1 |  | Y
F0.2 |  | Requirements freeze
F0.2.1 |  |  | Requirements consolidation | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | BA, PM | F0.1.1 | R2 |  | Y
F1 | UX & Functional Design
F1.1 |  | UX
F1.1.1 |  |  | User journeys and wireframes | 6 | 10 | 15 |  | 5 | 8 | 12 |  |  | UX, BA | F0.2.1 | R3 |  | Y
F1.1.2 |  |  | Accessibility design review | 2 | 3 | 5 |  | 2 | 3 | 5 |  |  | UX, QA | F1.1.1 |  |  | Y
F1.2 |  | Functional design
F1.2.1 |  |  | API & data contract design | 4 | 7 | 10 |  | 3 | 5 | 8 |  |  | TA, BE | F0.2.1 | R4 |  | Y
F2 | Core Build
F2.1 |  | Back-end
F2.1.1 |  |  | Back-end services and business logic | 20 | 30 | 45 |  | 20 | 30 | 45 |  |  | BE, TA | F1.2.1 | R4, R5 |  | Y
F2.2 |  | Front-end
F2.2.1 |  |  | Front-end implementation | 18 | 28 | 40 |  | 18 | 28 | 40 |  |  | FE, UX | F1.1.2, F1.2.1 | R3 |  | Y
F3 | Integrations
F3.1 |  | Registry integration
F3.1.1 |  |  | Registry integration | 6 | 10 | 15 |  | 6 | 10 | 15 |  |  | INT, BE | F1.2.1 | R5, R6 |  | Y
F3.2 |  | Payments integration
F3.2.1 |  |  | Payments integration | 7 | 12 | 18 |  | 7 | 12 | 18 |  |  | INT, BE | F1.2.1 | R6, R7 |  | Y
F3.3 |  | Case-management integration
F3.3.1 |  |  | Case-management integration | 5 | 9 | 14 |  | 5 | 9 | 14 |  |  | INT, BE | F1.2.1 | R6 |  | Y
F4 | Security & Accessibility Audit
F4.1 |  | Audit
F4.1.1 |  |  | Security testing | 4 | 6 | 10 |  | 4 | 6 | 10 |  |  | QA, TA | F2.1.1, F2.2.1, F3.1.1, F3.2.1, F3.3.1 | R8 |  | Y
F4.1.2 |  |  | Accessibility audit | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | QA, UX | F2.2.1 | R9 |  | Y
F5 | Internal Acceptance
F5.1 |  | Internal QA
F5.1.1 |  |  | Regression and integration test cycles | 6 | 9 | 14 |  | 6 | 9 | 14 |  |  | QA, BE | F4.1.1, F4.1.2 |  |  | Y
F6 | UAT
F6.1 |  | UAT support
F6.1.1 |  |  | UAT execution support and defect fixing | 8 | 14 | 22 |  | 8 | 14 | 22 |  |  | BE, FE, PM | F5.1.1 | R10 |  | Y
F7 | Production Deployment
F7.1 |  | Deploy
F7.1.1 |  |  | Production deployment | 3 | 5 | 8 |  | 3 | 5 | 8 |  |  | DEVOPS, BE | F6.1.1 | R11 |  | Y
F7.1.2 |  |  | Hypercare and documentation handover | 4 | 7 | 10 |  | 4 | 7 | 10 |  |  | DOC, PM, BE | F7.1.1 |  |  | Y
TOTAL

## Pianificazione Risorse
Ruolo | Codice | Tipo | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | TOTALE (PD)
|  | Settimana del | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21
Business Analyst | BA | billable | 2.58 | 2.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Back-end Developer | BE | billable | 0 | 0 | 0 | 0 | 0 | 3.08 | 3.08 | 3.08 | 3.08 | 3.08 | 3.08 | 3.08 | 3.08 | 3.08 | 3.08 | 0 | 0 | 0 | 3.58 | 3.58 | 3.58 | 3.58 | 0 | 0 | 0
DevOps Engineer | DEVOPS | billable | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.29 | 1.29 | 1.29 | 1.29
Technical Writer | DOC | billable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.75 | 1.75 | 1.75 | 1.75
Front-end Developer | FE | billable | 0 | 0 | 0 | 0 | 0 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Integration Specialist | INT | billable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.94 | 3.94 | 3.94 | 3.94 | 3.94 | 3.94 | 3.94 | 3.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Manager | PM | billable | 1.58 | 1.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quality Assurance | QA | billable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.83 | 6.94 | 6.94 | 3.11 | 0 | 0 | 0 | 0 | 0 | 0
Technical Architect | TA | billable | 0 | 0 | 2.33 | 2.33 | 2.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UX Designer | UX | billable | 0 | 0 | 4.44 | 4.44 | 4.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTALE settimana
Warning capacity
Overcommit: W17 (QA) (6.9 PD vs 5.0 PD capacity)
Overcommit: W18 (QA) (6.9 PD vs 5.0 PD capacity)

## Rischi
ID | Risk Description | Category | Affected Phases | Probability (1-5) | Impact (1-5) | Risk Score | Priority | Strategy | Mitigation Action | Owner | Contingency (pd) | Contingency Cost
R1 | Environment access delayed by IT bureaucracy | Organizational | F0 | 3 | 3 |  |  | Mitigate | Submit access requests in week -2 and track weekly | PM | 2
R2 | Requirements not frozen by stakeholders in time | Organizational | F0, F1 | 3 | 4 |  |  | Mitigate | Use a written sign-off gate before F1 starts | PM | 4
R3 | Accessibility findings force UX rework | Technical | F1, F2 | 3 | 3 |  |  | Mitigate | Run accessibility review in F1 instead of waiting for audit | UX | 5
R4 | API contract instability with internal data owners | Technical | F1, F2 | 4 | 3 |  |  | Mitigate | Lock API contracts at end of F1 with both data owners | TA | 6
R5 | Business logic complexity underestimated | Technical | F2 | 3 | 4 |  |  | Accept | Buffer included in pessimistic estimates of F2.1 | BE | 5
R6 | Integration vendor SLAs differ — one slow to deliver | External | F3 | 4 | 4 |  |  | Mitigate | Stub the slow integration in F2 and integrate late | INT | 8
R7 | Payments integration security review extra round | Technical | F3, F4 | 3 | 4 |  |  | Mitigate | Pre-review of payments flow in F1 with security team | INT | 4
R8 | Security audit findings require code rework | Technical | F4, F5 | 3 | 4 |  |  | Mitigate | Apply security checklist throughout F2 to reduce findings | TA | 5
R9 | Accessibility audit finds gaps requiring UI rework | Technical | F4, F5 | 3 | 3 |  |  | Mitigate | Continuous accessibility checks during F2 front-end work | UX | 4
R10 | UAT defect rate exceeds expectations | External | F6 | 3 | 4 |  |  | Mitigate | Pre-UAT walkthrough with the client before window opens | PM | 6
R11 | Production deploy fails the release window | External | F7 | 2 | 5 |  |  | Mitigate | Run a full dry-run deployment in pre-prod 1 week earlier | DEVOPS | 3
TOTAL
Management Reserve

## Riepilogo
Phase | Description | Best Effort (pd) | Likely Effort (pd) | Worst Effort (pd) | PERT Effort (pd) | Best Duration (d) | Likely Duration (d) | Worst Duration (d) | PERT Duration (d) | σ Duration
Project kickoff, environment validation, requirements freeze
User journeys, wireframes, accessibility-first design
Front-end and back-end implementation of the portal
Three integrations with internal authoritative sources, parallel with F2
Independent audit gate before UAT
Internal QA pass before client UAT
Client-side User Acceptance Testing window
Production rollout and 2-week hypercare window
TOTAL
Tech PERT Effort (PD)
PM Overhead (+10%) (PD)
DevOps Overhead (+5%) (PD)
Subtotale Tech + Overhead (PD)
Contingency per-rischio (PD)
Fascia BASSA
Management Reserve (20%) (PD)
Fascia MEDIA (raccomandata)
Fascia ALTA
Effort Billable Totale (PD)
Quota Billable
Durata Calendario (settimane) | 25
Effort per Team (PD)
Build | 105
Delivery | 22.3333
Design | 13.3333
Operations | 7.1667
Quality | 20.8333
Scenari di Sensitivity
Optimistic: ~85% of Fascia MEDIA if integration vendors deliver on schedule and audit finds no major issues
Realistic: Fascia MEDIA — current best estimate including overhead and MR
Pessimistic: ~120% of Fascia MEDIA if integration vendor delays compound and require UAT rework